## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Common | user | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | Hồng Anh | To Do | iter1
2 | Demo Dashobard | Common | user |  | Hồng Anh | To Do | iter1
3 | User Login | Common | user | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | Hồng Anh | To Do | iter1
4 | Password Reset | Common | user | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | Đan | To Do | iter1
5 | User Register | Common | user | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | Đan | To Do | iter1
6 | User Profile | Common | user | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | Đan | To Do | iter1
7 | Password Change | Common | user | Fields: Current Password, New Password, Verifying Password | Tuấn | To Do | iter1
8 | Setting List | Admin | admin | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | Tuấn | To Do | iter1
9 | Setting Details | Admin | admin | Fields: Type (L), Title, Value, Display Order, Status, Description | Tuấn | To Do | iter1
10 | User List | Admin | admin | Filters: Role, Status Column: Id, Full Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Full Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | Minh | To Do | iter1
11 | User Details | Admin | admin | Fields: Id, Full Name, Email, Mobile, Role, Status, Note | Minh | To Do | iter1
12 | Subject List | Manager | manager, admin | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | Minh | To Do | iter1
13 | Subject Details | Manager | manager, admin | Fields: Code, Name, Manager (L), Expert (L), Status, Description | Chương | To Do | iter1
14 | Web Contact List | Supporter | supporter, admin | Show the list of assigned web contacts | Chương | To Do | iter1
15 | Web Contact Details | Supporter | supporter, admin | View/Edit an assigned web contact | Chương | To Do | iter1

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | Hồng Anh | To Do
2 | Demo Dashobard | Common |  | Hồng Anh | To Do
3 | User Login | Common | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | Tuấn | To Do
4 | Password Reset | Common | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | Minh | To Do
5 | User Register | Common | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | Đan | To Do
6 | User Profile | Common | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | Hồng Anh | To Do
7 | Password Change | Common | Fields: Current Password, New Password, Verifying Password | Chương | To Do
8 | Setting List | Admin | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | Tuấn | To Do
9 | Setting Details | Admin | Fields: Type (L), Title, Value, Display Order, Status, Description | Tuấn | To Do
10 | User List | Admin | Filters: Role, Status Column: Id, Full Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Full Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | Minh | To Do
11 | User Details | Admin | Fields: Id, Full Name, Email, Mobile, Role, Status, Note | Minh | To Do
12 | Subject List | Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | Chương | To Do
13 | Subject Details | Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | Chương | To Do
14 | Web Contact List | Supporter | Show the list of assigned web contacts | Đan | To Do
15 | Web Contact Details | Supporter | View/Edit an assigned web contact | Đan | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document